## Action Plan
Angiolini Working Group - Action Plan
ID | Recommendation | Theme linked to Action | Action | Action Update | Action Owner
[6 empty] | Milestone | RAG | C & C | PPC | People | ARAC
AWG ACTION_001 | 42. The PIRC should conduct an annual audit of triage within PSD of public complaints against the police to ensure that matters that can be resolved by FLR, or misconduct, or potential criminality are being properly identified and routed accordingly, and to provide assurance that Article 3 and Article 5 cases are being correctly identified and reported forthwith to COPFS. | Audit & review | Develop joint PIRC/SPA annual audit process (first audit to address this recommendation) | Pending discussions at NCDHG and PS Exec, meeting to take place between PIRC/SPA to establish audit methodology | Complaints (via NCHDG) | tbc (dependent on NCHDG) |  | y
AWG ACTION_002 | 61. Both PS and the PIRC should consider drawing on the expertise of Audit Scotland and the Scottish Public Services Ombudsman in re‑designing the audit arrangements in respect of police complaints. | Audit & review | See Action 001 | See Action 001 | See Action 001 | See Action 001 |  | y
AWG ACTION_003 | PR5. Frontline resolution of complaints should be subject to close and regular monitoring through regular, meaningful internal and external audits, and monitoring of decision making. | Audit & review | See Action 001 | See Action 001 | See Action 001 | See Action 001 |  | y
AWG ACTION_004 | PR27. All the audit arrangements, including regular dip sampling, designed to identify poor practice, good practice and emerging trends should be prioritised and co-ordinated to support the common objective of improving standards and service to the public. | Audit & review | See Action 001 | See Action 001 | See Action 001 | See Action 001 |  | y
AWG ACTION_005 | 26. PIRC should work collaboratively with the SPA to agree and embed a proportionate and effective approach to preliminary assessment (for Regulation 8 of the senior officer conduct regulations) until such time as new regulations come into effect. | Conduct & standards | 1. Revise SPA Guidance on Conduct Regulations in respect of preliminary assessment in accordance with this earlier narrative in Preliminary Report. 2. Liaise with PIRC to consider further developments in line with this recommendation, and update SPA Guidance accordingly. | 1. Revised Guidance developed and subjected to PIRC/SCOPSA consultation prior to Final Report. 2. Meeting with PIRC scheduled for 5 May. Any further changes to Guidance to be incorporated with a view to presenting final version to August Committee. | Complaints | 2021-08-19 |  | y
AWG ACTION_006 | PR16. Complaints against senior officers should be prioritised and dealt with, by both the PIRC and the SPA, as speedily as is reasonable, because of the destabilising impact a prolonged investigation can have. | Conduct & standards | Amend SPA Complaint Handling Procedures to reflect priority to be given to complaints about senior officers | Revised Complaints Handling Procedures developed and subjected to PIRC/SCPOSA consultation prior to Final Report. To be presented to August Committee. | Complaints | 2021-08-19 |  | y
AWG ACTION_007 | PR18. The range of options available to the SPA when a senior police officer is under investigation under the conduct regulations should be clarified and expanded, to provide alternatives to suspension. | Conduct & standards | Amend SPA Guidance on Conduct Regulations to make clear the range of alternatives to suspension. | See Action 005 | See Action 005 | See Action 005 |  | y
AWG ACTION_008 | PR19. Any process for preliminary assessment of senior officer misconduct should require the relevant authority both to take into account whether the allegation is made anonymously, is specific in time and location, or whether it appears, on the face of the allegation, to be either vexatious or malicious. SG should consider amending the conduct regulations to reflect this process. | Conduct & standards | Update SPA Guidance on Conduct Regulations to reflect points made in the review. | See Action 005 | See Action 005 | See Action 005 |  | y
AWG ACTION_009 | 68. The SOG or NCHDG should take an early opportunity to engage with the SPSO to agree where their contribution and advice would be most useful. | Efficiency & Effectiveness | Engage with SPSO via SOG / NCHDG |  | Complaints (via NCHDG/SOG) | tbc (dependent on NCHDG/SOG) |  | y
AWG ACTION_010 | PR13. SG should consider the case for amending the legislation to include a provision to deal with vexatious complainers | Efficiency & Effectiveness | Participate in joint review of partner 'Unacceptable, Persistent or Unreasonable Actions by Complainers Policy' via NCHDG to ensure consistency. | Meeting of NCHDG on 13 May will seek to finalise this work, with a view to presentation of revised SPA Policy to August Committee | Complaints (via NCHDG) | 2021-08-19 |  | y
AWG ACTION_011 | 5. PS and SPA should consider expanding the collection of diversity data and the publication of information in order to enhance their understanding, and public understanding, of attitudes and concerns in different communities. | Equality, diversity & inclusion | Review complaints forms to enable understanding of diversity of complainants | Discussions taking place via NCHDG re consistent approach to E & D forms. SPA review of online forms being progressed as part of wider review of SPA digital offer. | Complaints / Strategic Business Management / SOG | 30/09/2021 (although NB dependecy on NCHDG) |  | y
AWG ACTION_012 | 16. PS should implement, where it is in their gift, the SEMPER Scotland proposal that the composition of panel members for disciplinary hearings should be more diverse. | Equality, diversity & inclusion | Ensure, as far as possible, diversity of Police Appeals Tribunals (albeit Lord President appoints pool of members from which SPA selects). |  | Legal | Ongoing, as applicable | Complete | y
AWG ACTION_013 | 17. Appropriate support for anyone in PS who is the subject of internal or external discrimination should be enhanced. | Equality, diversity & inclusion | Engage with PS to ensure applicability of support for those working in SPA Corporate/Forensics |  | Workforce Governance | tbc (dependent on PS) |  |  |  | y
AWG ACTION_014 | 29. The SPA Complaints and Conduct Committee should hold PS to account for delays in investigations into complaints and misconduct. Where there is evidence of excessive delays in PIRC investigations having an effect on policing in Scotland the Committee should raise the matter with the Commissioner. | Governance & accountability | Liaise with PS to agree proposed content and timing of data required, with report to be submitted to Committee seeking their agreement (albeit recognising scope for ongoing development thereafter). | Engagement taken place with Members, SPA officials and PIRC, and ongoing engagement with PS on proposed content of future reports, with a view to incorporation from Q1 report onwards. | Complaints | 2021-08-19 |  | y
AWG ACTION_015 | 59. In order to ensure public confidence in the police, the SPA should confirm each year in its annual report whether or not in its view, based on an informed assessment by the Complaints and Conduct Committee and evidence from the relevant audits, the Chief Constable has suitable complaint handling arrangements in place. | Governance & accountability | Include confirmation in 2021/22 Annual Report, based on assessment by Committee during the preceding 12 months, and based on consultation with the PIRC | Any confirmation of the suitability of PS arrangements will require to be based on an assessment by the Complaints and Conduct Committee, as well as consultation with the PIRC. Given dependency on other actions set out in this plan, it is proposed that this be identified for completion via 2021/22 ARA | Complaints | Q1 22/23 Committee meeting date |  | y
AWG ACTION_016 | 79. The SPA Complaints and Conduct Committee should scrutinise PS performance in dealing with complaints and hold the service to account where the targets are not being achieved. | Governance & accountability | See Action 014 | See Action 014 | See Action 014 | See Action 014 |  | y
AWG ACTION_017 | PR26. There should be the immediate establishment of a senior cross-agency joint Working Group involving the SPA, Police Scotland and the PIRC to develop appropriate and up to date guidance. | Governance & accountability |  | Complete - cross-agency Strategic Oversight Group and National Complaints Handling Development Group established. Regular updates provided to Committee |  | n/a | Complete | y
AWG ACTION_018 | 32. SPA and PS should consider together what role the SPA Complaints and Conduct Committee, or the Policing Performance Committee, might have in relation to the discussion of ethical issues in policing in Scotland. | Rights & ethics | Develop Framework settting out SPA approach to oversight of ethhical issues. | Discussion to take place between SPA functional heads to discuss respective responsibilities and consider what an ‘ethics framework’ for the SPA could look like, before engaging with PS to explore potential for development of a joint framework. Produce plan to progress development of a draft Framework, prior to presentation to the two Committee Chairs for consideration and wider discussion with PS . | Change & Operational Scrutiny | 28/05/2021 (to establish plan) |  | y | y
AWG ACTION_019 | 70. Independent Custody Visitors should, as a matter of course, check with custody officers and with detainees that a third party has been notified of their detention. | Rights & ethics |  | Complete - Visitors are already trained to ask if a 3rd party has been notified and to confirm this with custody officers and staff. This is also set out in the 'aide memoire' checklist provided for use during visits. |  | n/a | Complete |  | y
AWG ACTION_020 | 1. PS Code of Ethics should be given a basis in statute. SPA and the Chief Constable should have a duty jointly to prepare, consult widely on, and publish the Code of Ethics, and have a power to revise the Code when necessary. | Rights & ethics | Explore potential for joint work on the Code in advance of legislative change (including potential to widen scope to have a Code which applies to the wider SPA/PS workforce). (See also Action 18) |  | Workforce Governance | tbc (dependent on partners) |  |  |  | y
AWG ACTION_021 | 20. PIRC should be added to the list of prescribed persons in The Public Interest Disclosure (Prescribed Persons) Order 2014 in order that people working in PS and SPA are able to raise their concerns with an independent third-party police oversight organisation. | Rights & ethics | Explore (through discussion between SPA, PS and PIRC) scope to identify PIRC as an external organisation to whom individuals can rase concerns, in advance of legislative change formally adding them to the list of prescribed persons |  | Workforce Governance | tbc (dependent on partners) |  |  |  |  | y
AWG ACTION_022 | 21. Whistleblowing can be an indicator of what is happening within an organisation and therefore PS should review and audit its whistleblowing arrangements and data on a regular basis. | Rights & ethics | Introduce regular process for review and audit of SPA whistleblowing arrangements and data on a regular basis. | SPA Whistleblowing Guidance was updated in March 2020, with governance and reporting arrangements, in line with this recommendation, included. A first annual report (which includes a self-assessment against best practice), will be presented to July ARAC (following which this action will be marked as complete, moving into BaU arrangements). | Workforce Governance | 2021-07-15 |  |  |  |  | y
AWG ACTION_023 | 62. PS should appoint a PSD training officer to maintain the momentum in training and development arising from its internal Risk, Assurance and Inspection (RAI) team audit, and to liaise with the SPSO, the PIRC and the SPA on joint training, best practice and other relevant development opportunities. | Training & HR | Engage in joint development opportunities via NCHDG |  | Complaints (via NCHDG) | tbc (dependent on NCHDG) |  | y
AWG ACTION_024 | 65. PIRC and PS should work together to develop training and development opportunities that take the theoretical learning from thematic analysis of complaints and embed it in practical learning for individual officers. | Training & HR | Input to development of practial learning opportunities via NCDHG. |  | Complaints (via NCHDG) | tbc (dependent on NCHDG) |  | y
AWG ACTION_025 | PR4. PS should scrutinise complaints thoroughly on receipt so as to ensure that grievance matters that would in any other walk of life be treated in an HR context are not artificially elevated and dealt with as conduct matters. | Training & HR | Amend SPA Complaints Handling procedures to state that, in general, HR-related complaints are dealt with, in the first instance, as grievances. | See Action 006 | See Action 006 | See Action 006 |  | y
AWG ACTION_026 | PR10. PS should consider the importance of providing all officers involved in frontline resolution with training in mediation and customer handling. | Training & HR | Consider mediation training for SPA Complaints Team, seeking access to PS provision where applicable | Pre-COVID, PS were designing a CPD programme of events for delivery during 2020, for which invitations would be extended to SPA Complaints team. This was then paused, with proposals being developed to deliver training remotely. | Complaints (via PS) | tbc (dependent on PS) |  | y
AWG ACTION_027 | PR17. Further training for complaints and conduct officers in SPA should be consolidated and broadened in order to ensure the right skillset and up to date knowledge of complaint handling best practice in other sectors. | Training & HR | Develop programme of training and personal development for the SPA Complaints Team, seeking access to PIRC/PS provision where applicable (see Action 23 & 26) | PDPs in place for SPA Complaints team for 2020/21, although acknowledging impact of COVID and current team manager absence. PDPs to be reviewed and updated as part of 2021/22 PDR process. See Action 23 & 26 in terms of partner training) | Complaints | 31/03/2022 (noting dependencies) |  | y
AWG ACTION_028 | 30. To increase public confidence in the system the SPA Complaints and Conduct Committee should consider using its minutes as a means of sharing with the public more of their substantive discussions and how PS is being held to account in this area; and consider whether some content of the minutes of the private sessions, where some strategic and policy matters are discussed, could be included in the published minutes. | Transparency & accessibility | Develop proposed approach to publication of private Committee discussions where applicable, whilst ensuring appropriate safeguards in place. | Proposed approach being tabled at May Committee meeting seeking agreement to adopt going forwards. | Complaints / Strategic Business Management | 2021-05-19 |  | y
AWG ACTION_029 | 31. The SPA Complaints and Conduct Committee's scrutiny function should be reported on in the SPA annual report, drawing out particular trends, highlighting improvements or concerns and using complaints data as an indicator of communities' satisfaction or dissatisfaction with policing services | Transparency & accessibility | Develop a Committee-specific 2020/21 annual report, and summary extract for inclusion in SPA Annual Report (albeit recognising scope for ongoing development thereafter, particularly in light of progression of other actions outlined in this plan). | Proposal to be developed following May meeting (to incorporate consideration of SPA/PS Q4 and Committee effectiveness reports), and presented to August Committee (text for ARA to be agreed by correspondane in advance depending on timescales) | Complaints | 2021-08-19 |  | y
AWG ACTION_030 | 46. The ability to report directly to the CAAPD of COPFS a complaint of a crime by a police officer should be much better publicised and made more accessible to the public by COPFS, by PS and by the PIRC. | Transparency & accessibility | Publicise role of CAAPD via SPA website. | Engage with partners via July NCHDG sub-group with a view to agreeing consistent approach in advance of updating website. Aim to complete prior to Aug Committee | Complaints / Strategic Business Management | 2021-08-19 |  | y
AWG ACTION_031 | PR8. PS should simplify and streamline systems to make it as straightforward as possible for members of the public to navigate this rather opaque landscape and as easy as possible for them to access and understand information on how to make a complaint. In particular the online complaints form on the PS website should be made more prominent. | Transparency & accessibility | 1. Assess prominence given to complaints on SPA website and ensure clarity provided on kinds of complaint which SPA can deal with 2. Review online complaints form to ensure provides simplest possible means of making a complaint. | 1. Complete - SPA Complaints web page updated and simplified, now showing what we do and do not do, with links and contact details on one page. 2. See Action 11 | Complaints /Strategic Business Management | 2021-09-30 |  | y
The following were commented upon in the report, but did not amount to formal recommendations:
| I believe that the two functions below are the significant responsibilities that the Complaints & Conduct Committee should focus on in future: “(iii) Monitor the handling of relevant complaints by SPA and PS, seeking information on themes or trends as appropriate, with a view to the Committee satisfying itself that the arrangements maintained by SPA and PS for the handling of relevant complaints are suitable.” “(ix) Critically examine reports from HMICS, PIRC, and any other information provided by PS in relation to complaints about the police, and ensure that appropriate improvement plans are implemented or remedial action is taken within agreed timescales.” | n/a | Incorporate within Review of Committee Effectiveness process from 21/22 onwards |  | Complaints | tbc (per 21/22 Review process) |  | y
| I also believe that the oversight role of the Committee could be enhanced if members were able to see at first hand areas of policing activity relevant to their remit. Where time and resources allow, the members should seek further opportunities to engage with policing in Scotland or engage with other authorities across the UK carrying out similar oversight functions. |  | 1. Engage with PS to explore opportunities to observe relevant areas of policing activity. 2. Identify other authorities across UK carrying out similar oversight functions, and explore means of engaging. |  | Complaints | 2021-08-19 |  | y
| It is clearly vital therefore that those carrying out that responsibility for SPA (holding PS to account for the efficacy and effectiveness of its complaints handling practices) are knowledgeable in appropriate complaint handling standards and responses. Both staff and members of the Complaints and Conduct Committee should receive appropriate training to allow them to carry out their functions. The SPA complaints staff should be familiar with model complaint handling procedures published by SPSO and keep up to speed with developments so that they can brief SPA members on best practice and developments in this field. | n/a | 1. Develop and deliver Committee-specific Member development activity (upon induction and thereafter as required) 2. See Action 27 in respect of SPA staff | 1. Member induction plan currently being implemented. Undertake analysis thereafter to identify further development needs and ensure ongoing consideration on at least an annual basis 2. See Action 27 | Complaints / Workforce Governance | 1. tbc following induction 2. See Action 27 |  | y
| Arrangements for handling anonymous complaints should be set out in policy and, as with any other complaint, the starting point should be that the allegation should be treated with an open mind…. The response needs to be proportionate based on an assessment of the reliability and credibility of the information provided and the individual complaining, as far as that is possible, as well as the seriousness of the allegations. Because of the very nature of anonymity these complaints require to be treated with caution because of the potential false, vexatious and defamatory nature of the allegation. | n/a | Amend SPA Complaints Handling procedures to include guidance for handling anonymous complaints, incorporating the factors suggested by the review. | See Action 006 | See Action 006 | See Action 006 |  | y
| SPA may want to target volunteers who could do night visits. SPA could provide safe transport to and from the police station if required. ICVs should also be making visits at times when detainees are at their most vulnerable and should be encouraged to get the full picture of how custody suites operate throughout the night and day. | n/a | Explore options to enable nightime visits, in line with the recommendation | Currently exploring potential to further digitise the custody visiting scheme, which would enable remote nightime visits. | ICVS | tbc (dependent on ICT & wider engagement) |  |  | y
Green = On-schedule / expected to deliver according to Plan
Amber = Slippage / issues but corrective action expected to maintain progress close to Plan
Red = Serious problems - delivery date unachievable / schedule to be revised